## Sheet1
Session | [5 empty] | Function of main focus in session |  |  | Another function of major focus in session |  |  | Verifiable records -- can be used to check log information later!
Group's user id | Work Start Date | Work start time | Initials of students present | Session duration minuted | Exercise | Directory | Fle name | Function in file | Directory | Fle name | Function in file | Estimated number of code lines written/altered. | How many relevant test cases still FAIL | How many relevant test cases pass | Final line of make check output | Tag used to commit work in repository
group41 | 2017-08-28 | 0:30 | HV, AR, UD | 4HOURS | T02 | threads | thread.c | thread_set_priority() thread_get_priority() sema_up sema_down | threads | synch.c | N/A | 15 | 9 | 3 | 16 of 50 tests still FAIL | T02 TASK 1
group41 | 2017-08-29 | 6:00 | HV, AR, UD | 3 Hours | T02 | threads | thread.c | lock acquire lock release cond_wait | threads | synch.c |  | 50 | error | error | error | some more changes for t02
Group 41 | 30/08/2017 | 42981.75 | HV, AR, UD | 4HOURS | T02 | threads | thread.c | sema_up sema_down lock_acquire lock_release cond_wait | Threads | synch.c |  | Around 150 | ERROR | ERROR | ERROR | FEW MORE CHANGES
Group 41 | 31/08/2017 | 42981.9167 | HV, AR, UD | 4Hours | T02 | threads | thread.c | sema_up sema_down lock_acquire lock_release cond_wait | Threads | synch.c |  | Around 150 | 0 | 12 | 7 OF 27 TESTS FAIL | T02
Group 41 | 2017-02-09 | 42981.7917 | HV, AR, UD | 2Hours | T03 | Read theory | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Read theory | Read theory
Group 41 | 2017-05-09 | 42983.4167 | HV, AR, UD | 4 Hours | T03 | threads | thread.c | thread_calculate_load_avg() thread_get_recent_cpu() | devices | timer.c | timer_interrupt | 50 | 6 | 1 | 6 OF 27 TESTS FAIL | T03 task 01
Group 41 | 2017-06-09 | 42984.4167 | HV, AR, UD | 2 Hours | T03 | Threads | thread.c | thread_calculate_recent_cpu() thread_calculate_priority() | Threads | thread.c | thread_calculate_recent_cpu_for_all() thread_calculate_priority_for_all() | 100 | 4 | 2 | 4 OF 27 TESTS FAIL | load-60 and load_avg